**Molonglo Substation Works on Coulter Drive 2022 - 2025**

|  |  |  |  |
| --- | --- | --- | --- |
| Period | Works | Responsible | Impacts |
| August– end of September 2022 | Connect underground cable from substation site eastward past cavaletti to Cook paddocks and under William Hovell Drive | SLA*Wodens* contractors | Area will be impassable until works complete |
| September 2022 - May 2023 | Construction of a compound on the substation site, including minor trenching, delivery of batteries, demountable buildings, cable hauling and perimeter security fence construction. | Evoenergy/ITPThe civil contractor has yet to be confirmed  | Access track will be busy during the week |
| Mid-October – end of December 2022  | Delivery of 18t cable drums, on site crane, traffic along access track to substation site | Evoenergy*Zinfra* contractors | Access track should be available on weekends |
| October 2022 – May 2023 | Delivery of 18t cable drums to Boundary Road, River Road (Arboretum) and along the Molonglo River | Evoenergy*Zinfra* contractors | Management Tracks in Arboretum & pine forest to the west |
| From May 2023 | Zinfra will dismantle the overhead transmission line towers between Kama reserve and the Tuggeranong Parkway.  | Evoenergy*Zinfra* contractors | Management Tracks in pine forest to the west of the Arboretum |
| 2024 - 2025 | Building construction on substation site, electrical equipment installation and connection to Evoenergy Network, security perimeter fence installation | Evoenergy | More info coming later |